## IMCA
List IMCA
No | Rack No. | Tahun | Description
2003
1 | 1 | 2003 | Gas Recycling During strat-up
2 | 2 |  | -
3 | 3 |  | -
4 | 4 |  | -
2004
1 | 5 | 2004 | Modification Droplet separator at E-851 (S-851)
2 | 6 | 2004 | Air Compressor C-991C
3 | 7 | 2004 | FOL Separation
4 | 8 | 2004 | Scrubbing Water Circulation in T-023
5 | 9 | 2004 | TK-822 as buffer feed WWT tank
6 | 10 | 2004 | Falling Film Evaporator
7 | 11 | 2004 | Additional Scrubbing Water line from T-022 to D-021
8 | 12 | 2004 | Pilot plant for hydrogenation reactor
2005
1 | 13 | 2005 | Unit particle removal from FOL
2 | 14 | 2005 | J-225 Condenser replacement
3 | 15 | 2005 | LPG Injection into reformer as feed stock addition
4 | 16 | 2005 | FOL purge controlling on Octanol plant
2006
1 | 17 | 2006 | Propylene vapoor recovery
2 | 18 | 2006 | PCV-7251A/B improvement
3 | 19 | 2006 | Additional H2SO4 stroge (TOT)
4 | 20 | 2006 | Corrosion and scalling facility
5 | 21 | 2006 | Additionalisolating valve at membrane 1st stage B bank
6 | 22 | 2006 | Compesation valve for FQI-4306, LI-7201, LI-7204
7 | 23 | 2006 | R-510 hydrohen recycle
8 | 24 | 2006 | Membrane offgas 2nd stage to C-018 suction recycle
9 | 25 | 2006 | Additional oxidizing biocide (gas chlor) injection facility
10 | 26 | 2006 | Utilize NBA Pump & line (P-722B) for 2EH transfer facility
11 | 27 | 2006 | LPG Vaporizing unit improvement
12 | 28 | 2006 | E-419 improvement (CW side system)
13 | 29 | 2006 | Pilot plant for hydrogenation NBA reactor
14 | 30 | 2006 | Oxo reactor pilot plant
15 | 31 | 2006 | PGL header liquid separation improvement
16 | 32 | 2006 | Biological control pond
17 | 33 | 2006 | Membrane offgas 2nd stage transfer to PSA
18 | 34 | 2006 | Addition of CO2 into syngas in order to increase finished product
2007
1 | 35 | 2007 | Additional motor safety sirine
2 | 36 | 2007 | Additional lighning protection
3 | 37 | 2007 | N2 blanketing system
4 | 38 | 2007 | Hydrogenation reactor interlock improvement
5 | 38A | 2007 | E-022B cooler (new add)
6 | 38B | 2007 | Increase total plant capacity to 115% from existing
2008
1 | 39 | 2008 | Additional LPG Storage
2 | 40 | 2008 | Additional smoke detector in Admin Building, Prod, MNTC & Catalyst shelter
3 | 41 | 2008 | Bypassing NG stream from FC014 to E-010B outlet
4 | 42 | 2008 | 3 stages of ejector in J-435 unit
5 | 43 | 2008 | Waste collector (TPS-B3)
6 | 44 | 2008 | Pre-reformer heating up systems
7 | 45 | 2008 | Recondition TK-831
8 | 46 | 2008 | Install Ex. J-435 ING to T-320 vacuum system
9 | 47 | 2008 | Increase C-011 capacity by lowering suction feed
10 | 48 | 2008 | Water pond for temporary receiving clean water from lorry truck
11 | 49 | 2008 | -
12 | 50 | 2008 | GHY recycle in R-610 system
13 | 51 | 2008 | CO2 injection automation valve
14 | 52 | 2008 | TK-853 intermittent blowdown control valve
15 | 53 | 2008 | Install control valve (AV-8102) on TK-814A
16 | 54 | 2008 | P-816 replacement
17 | 55 | 2008 | Modification XV-0102 & XV-0122 to HV-0121 & HV-0122 in R-012
18 | 56 | 2008 | MPS LPS header- DCS remote control valve
19 | 57 | 2008 | Liquid propylene unloading (jetty pipe line) modification
20 | 58 | 2008 | Membrane modification, add 2 new module on 2nd stage
21 | 59 | 2008 | TK-853 pit blowdown pump installation
22 | 60 | 2008 | T-520, T-530 crude aldehyde feed load trial
23 | 61 | 2008 | E-024C (replacement to SS304 material)
24 | 62 | 2008 | Improvement sequential starting up boiler
2009
1 | 63 | 2009 | P-974 oil separator water pump replacement
2 | 63A | 2009 | Control pH outlet WWT
3 | 64 | 2009 | Improvement unloading solvent 4B & 50
4 | 65 | 2009 | Improvent solid state to common timer (air dryer)
5 | 66 | 2009 | Provide deluge system bypass line for D-711 D-714 spherical tanks
6 | 67 | 2009 | Additional piping D-556 to TK-971
7 | 68 | 2009 | D-985 to TK-971 piping replacement
8 | 69 | 2009 | Suction cooler C-009 for recycle membrane off gas
9 | 70 | 2009 | Safety valve for line 2EH (Ex. NBA)
10 | 71 | 2009 | Replacement pipe E-983 to TK-811
11 | 72 | 2009 | Recycle off gas & oxo gas to reduce CO in H2
12 | 73 | 2009 | P-973 oil separator oil pump replacement
13 | 74 | 2009 | Improvement controller HV-0103
14 | 75 | 2009 | Buffer pond filter
15 | 76 | 2009 | Edg manual start & redundancy battery
16 | 77 | 2009 | Oil injection for damper of B-921
17 | 78 | 2009 | N2 blanketing for TK-942
18 | 79 | 2009 | R-510 for IBD hydrogen
19 | 80 | 2009 | Utilize P-931C as P-758 recycle water pump
20 | 81 | 2009 | Co guard bed PSA single
21 | 82 | 2009 | Installing P-021 old booster pump cooler E-024A and B
22 | 83 | 2009 | CO guard bed PSA permanent
23 | 84 | 2009 | Additional temperature instrument at PPL line
24 | 85 | 2009 | Installing tubing for make up drum press. Unit of A-110
25 | 85A | 2009 | Modification H2SO4 system in DMW unit
2010
1 | 86 | 2010 | Improve IBA loading line
2 | 87 | 2010 | Improve neutralizing TK-853
3 | 88 | 2010 | CNG receiving facility
4 | 89 | 2010 | Additional/ modification water sprayer on spherical tank
5 | 90 | 2010 | T-520 T-530 crude aldehyde column series *CANCELED AUG 2011
6 | 91 | 2010 | Boiler fuel solenoid protection improvement
7 | 92 | 2010 | Modification NGB of TK-721 and TK-722
8 | 93 | 2010 | Optimizing E-166 using RWS
9 | 94 | 2010 | Additional oil cooler C-112
10 | 95 | 2010 | 2EH product cooler
11 | 96 | 2010 | Install carbon filter at outlet D-931
2011
1 | 97 | 2011 | Modification PGL line from J-325
2 | 98 | 2011 | Additional bypass PC-1002A
3 | 99 | 2011 | Changing MPS with BFW for mixing cooling jacket syn gas compressors
4 | 100 | 2011 | Modification discharge line P-725B
5 | 101 | 2011 | Modification aldehyde recovery line
6 | 102 | 2011 | separator FNG boiler
7 | 103 | 2011 | Install temp. instrument at flue gas E-010B
8 | 104 | 2011 | Ignition system H-851 improvement
9 | 105 | 2011 | NBA line off spec
10 | 106 | 2011 | Increase pressure NG
11 | 107 | 2011 | Additional flow meter of FQI-7207
12 | 108 | 2011 | FM200 in capacitor banks room
13 | 109 | 2011 | Balancing load of TR-2 and TR-3
14 | 110 | 2011 | Artesian well FWS source
15 | 111 | 2011 | Upgrade PLC modicon PSA Membrane
2012
1 | 112 | 2012 | Additional new jetty
2 | 113 | 2012 | CO2 recovery plant
3 | 114 | 2012 | Additional Line Foam Hydrant
4 | 115 | 2012 | Additional line of waste water effluent
5 | 116 | 2012 | Additional NBA line for export (to jetty)
6 | 117 | 2012 | Replacing and additional housing bag filter on DMW unit
7 | 118 | 2012 | Additional line from J-325 to J-435
8 | 119 | 2012 | MDEA Ourification filter (F-023)
9 | 120 | 2012 | Pipeline into Laboratory replacement GHY UHP tube
2013
1 | 121 | 2013 | Sewer water filtration unit

## MOC
PT. PETRO OXO NUSANTARA
Progress of MOC (Management Of Change)
No. | Rack No. | MOC No | Project Name | Proposal | Approval | Complete | Operate | MOC Closed | Leader | Status | Type | ISO Register No. | Hazop | Remark
2013
1 | 122 | 001/MOC/OCT/IX/2013 | Double pipe E-165 | F | F | F | F | F | STY | F | O | 05/ISO/MOC/V/14 | OK
2 | 123 | 002/MOC/OCT/IX/2013 | Recovery NBA from FOL T-640 | F | F | F | F | F | STY | F | O | 03/ISO/MOC/XI/13 | OK
3 | 124 | 003/MOC/OCT/XII/2013 | Utilization of Waste Water (outlet TK-819) and Water Sewer | F | F | C | C | C | MAR | C | O | Cancel
4 | 125 | 004/MOC/OCT/XII/2013 | Bypass line for 2nd stage suction of C-150 | F | F | F | F | F | CHD | F | O | 04/ISO/MOC/XII/13 | IP
5 | 126 | 005/MOC/OCT/XII/2013 | Additional compensation for level indicator at intermediate tank | F | F | F | F | F | DNI | F | O | 09/ISO/MOC/XI/14 | IP
6 | 127 | 006/MOC/OCT/XII/2013 | Redundancy lube oil pump C-412 | F | F | F | F | F | CHD | F | O | 07/ISO/MOC/X/14 | IP
2014
1 | 128 | 007/MOC/UTL/I/2014 | Additional new package boiler | F | F | F | F | F | GPA | F | O | 10/ISO/MOC/XII/14 | IP
2 | 129 | 008/MOC/SGA/II/2014 | Reduce HSAS content in MDEA solution system | F | F | F | F | F | WSK | F | O | 08/ISO/MOC/X/14 | IP
3 | 130 | 009/MOC/UTL/IV/2014 | Additional flowmeter for PPL consumption | F | F | F | F | F | SLK | F | O | 06/ISO/MOC/VIII/14 | IP
4 | 131 | 010/MOC/UTL/VII/2014 | Additional artesian well pump | F | F | F | F | F | GPA | F | O | 15/ISO/MOC/V/16 | IP
5 | 132 | 011/MOC/SGA/IX/2014 | CO2 recovery and liquefaction plant | F | F | F | F | F | AJW | F | O | 50/ISO/MOC/VIII/21 | IP
6 | 133 | 012/MOC/UTL/X/2014 | Modification PGL line and flare stack area | F | F | F | F | F | EST | F | O | 10/ISO/MOC/III/15 | IP
7 | 134 | 013/MOC/OCT/XI/2014 | Additional Isolate Valve R-410 | F | F | F | F | F | EST | F | O | 11/ISO/MOC/III/15 | IP
8 | 135 | 014/MOC/UTL/XI/2014 | Install Tie In for Soft water system | F | F | F | F | F | MMI | F | O | 12/ISO/MOC/III/15 | IP
9 | 136 | 015/MOC/UTL/XI/2014 | Modification Suction line P-855 | F | F | F | F | F | EST | F | O | 13/ISO/MOC/III/15 | IP
10 | 137 | 016/MOC/UTL/XII/2014 | Install LPS line from header to CO2 plant | F | F | F | F | F | EST | F | O | 14/ISO/MOC/III/15 | IP
2015
1 | 138 | 017/MOC/UTL/I/2015 | Reverse Osmosis Unit | F | F | F | F | F | AJW | F | O | 17/ISO/MOC/VI/16 | OK
2 | 139 | 018/MOC/EI/III/2015 | Modification ignition system H-922 | F | F | C | C | C | DNI | C | C | Cancel | -
3 | 140 | 019/MOC/UTL/IV/2015 | Additional new chilled water unit | F | F | F | F | F | EST | F | O | 16/ISO/MOC/V/16 | IP
4 | 141 | 020/MOC/UTL/V/2015 | Additional new air dryer unit | F | F | F | F | F | APT | F | O | 18/ISO/MOC/VI/16 | IP
5 | 142 | 021/MOC/UTL/X/2015 | Additional new sand filter in suction P-931C | F | F | C | C | C | EST | C | O | Cancel | -
2016
1 | 143 | 022/MOC/UTL/VI/2016 | Utilizing reject RO Unit | F | F | F | F | F | GPA | F | O | 19/ISO/MOC/IX/2016 | IP
2 | 144 | 023/MOC/UTL/VII/2016 | Switch Load Power to EDG | F | F | F | F | F | SLK | F | O | 20/ISO/MOC/XI/2016 | IP
3 | 145 | 024/MOC/UTL/VIII/2016 | Additional ampere motor indication product pump at DCS | F | F | F | F | F | YMA | F | O | 22/ISO/MOC/VII/2017 | IP
4 | 146 | 025/MOC/UTL/IX/2016 | Modification of RO Unit | F | F | F | F | F | EST | F | O | 23/ISO/MOC/VII/2017 | IP
5 | 147 | 026/MOC/SGU/IX/2016 | Additional line and pump to make up MEA CO2 gas | F | IP | IP | IP | IP | YUL | F | O | 30/ISO/MOC/V/2018
6 | 148 | 027/MOC/UTL/IX/2016 | Modification of circulation line PPL liquid from P-711B | F | F | F | F | F | EST | F | O | 51/ISO/MOC/VIII/2021
7 | 149 | 028/MOC/UTL/IX/2016 | Installing Ex. Old chiller pump as P-853B | F | F | F | F | F | EST | F | O | 24/ISO/MOC/VII/2017 | IP
8 | 150 | 29/MOC/UTL/IX/2016 | Improvement system of TK-855 | [8 empty] | Cancel | bar: F to O
9 | 151 | 030/MOC/UTL/IX/2016 | Modification line chemical injection Boiler P-925A/B | F | F | F | F | F | GPA | F | O | 21/ISO/MOC/XI/2016
10 | 152 | 031/MOC/UTL/XI/2016 | Switching P-751 B as main fire pump instead P-751 A | F | C | C | C | C | AJW | C | O | Cancel
11 | 153 | 032/MOC/SGA/IX/2016 | Install Oil Collector at CO2 Liquefaction System | F | F | F | F | F | YUL | F | H | 31/ISO/MOC/V/2018
12 | 154 | 033/MOC/UTL/XII/2016 | Additional line water from fish pond to TK-931 | F | F | F | F | F | EST | F | O | 25/ISO/MOC/XI/2017
13 | 155 | 034/MOC/UTL/XII/2016 | New E-719 (PPL cooler) | F | F | F | F | IP | YMA | F | O | 39/ISO/MOC/IV/2021
2017
1 | 156 | 035/MOC/UTL/I/2017 | Plant automation valve | F | F | F | F | F | MMI | F | O | 26/ISO/MOC/XII/2017
2 | 157 | 036/MOC/SG/VI/2017 | Additional interlock C-011/018 | F | F | F | F | F | SLK | F | O | 33/ISO/MOC/V/2018
3 | 158 | 037/MOC/SGU/VIII/2017 | Modification line to clean AFC E-018 | F | F | F | F | F | YUL | F | O | 34/ISO/MOC/V/2018
4 | 159 | 038/MOC/OCT/VIII/2017 | Additional filter at line after FC-4305 | F | F | F | F | IP | EST | F | O | 43/ISO/MOC/V/2021
5 | 160 | 039/MOC/UTL/VIII/2017 | Additional New pump P-931D (Feed RO Unit) | F | F | F | F | F | EST | F | O | 27/ISO/MOC/XII/2017
6 | 161 | 040/MOC/UTL/IX/2017 | Install ejector | F | F | F | F | F | EST | F | O | 44/ISO/MOC/V/2021
7 | 162 | 041/MOC/UTL/IX/2017 | Connecting cable to information system from 3D trasar to DCS | F | F | F | F | F | GPA | F | O | 28/ISO/MOC/XII/2017
8 | 163 | 042/MOC/UTL/IX/2017 | Additional of F-412A (series with existing F-412) | F | F | F | F | F | MMI | F | O | 29/ISO/MOC/XII/2017
9 | 164 | 043/MOC/OCT/IX/2017 | Modification line FWS to spray AFC E-425 | F | C | C | C | C | EST | C | O | Cancel
10 | 165 | 044/MOC/OCT/X/2017 | Modification of line P-511A | F | IP | IP | IP | IP | YMA | C | O | Cancel
11 | 166 | 045/MOC/OCT/X/2017 | Additional of filter F-411 (inlet D-411) | F | F | F | F | F | EST | F | O | 45/ISO/MOC/V/2021
12 | 167 | 046/MOC/OCT/XI/2017 | Additional filter F-417 (discharge P-417B) | F | F | F | F | F | YMA | F | O | 32/ISO/MOC/V/2018
13 | 168 | 047/MOC/SGA/X/2017 | DCS control LC-0281 (C-018 separator) | F | F | F | F | F | DNI | F | O | 37/ISO/MOC/VII/2019
2018
14 | 169 | 048/MOC/EI/IV/2018 | Upgrade combustion control for H-921 | F | C | C | C | C | SAM | C | O | Cancel | - | Replace with MOC No. 056/MOC/SGU/XI/2018
15 | 170 | 049/MOC/UTL/III/2018 | Modification of circulation line PPL liquid from E-719 | F | F | F | F | F | EST | F | O | 35/ISO/MOC/VIII/2018
16 | 171 | 050/MOC/SGU/IV/2018 | Additional line feed stock from stack H-922 | F | F | F | F | F | YSY | F | O | 46/ISO/MOC/V/2021
17 | 172 | 051/MOC/OCT/IV/2018 | Additional line of chilled water to E-166 (double pipe T-160) | F | C | C | C | C | EST | Hold | O |  | -
18 | 173 | 052/MOC/OCT/V/2018 | Provide facility to spray water at AFC E-118 | F | F | F | F | F | YMA | F | O | 36/ISO/MOC/IV/2019
19 | 174 | 053/MOC/ME/IX/2018 | Additional new separator D-417 | F | F | F | F | F | DRA | F | O | 52/ISO/MOC/VIII/2021
20 | 175 | 054/MOC/SG/IX/2018 | Modify outlet line R-012 | F | F | F | F | F | YSY | F | O | 47/ISO/MOC/V/2021
21 | 176 | 055/MOC/SGU/XI/2018 | Provide direct line SCI as fuel | F | F | F | F | F | MSY | F | O | 40/ISO/MOC/IV/2021
22 | 177 | 056/MOC/SGU/XI/2018 | Installation new boiler H-923 to replace H-921 | F | F | F | F | F | DRA | F | O | 53/ISO/MOC/VIII/2021
2019
23 | 178 | 057/MOC/SGU/II/2019 | Additional of separator on CO2 liquid compressor | F | F | F | F | F | CHD | F | O | 48/ISO/MOC/V/2021
24 | 179 | 058/MOC/EI/III/2019 | Upgrade Scada PSA/Membrane | F | F | F | F | F | DNI | F | O | 49/ISO/MOC/V/2021
25 | 180 | 059/MOC/SGU/V/2019 | Evonik Trial Membrane | F | F | F | F | F | MMI | F | O | 41/ISO/MOC/IV/2021
26 | 181 | 060/MOC/UTL/VII/2019 | Additional of P-855 B | F | F | F | F | F | DNI | F | O
27 | 182 | 061/MOC/OFF/VII/2019 | Manufacture of convenyor drumming units | F | F | F | F | F | MKH | F | O | 54/ISO/MOC/IX/2021
28 | 183 | 062/MOC/LCO2/VIII/2019 | Additional Boiler Fluegas Scrubber | F | C | C | C | C | YMA | IP | O | IP | - | Finished 2023
29 | 184 | 063/MOC/OCT/XI/2019 | Modification FOL system | F | F | F | F | F | MSY | F | O | 56/ISO/MOC/XI/2022
30 | 185 | 064/MOC/UTL/XII/2019 | RO to Mixed Bed Polisher | F | F | F | F | F | YSY | F | O | 42/ISO/MOC/IV/2021
31 | 186 | 065/MOC/OCT/XII/2019 | By Pass R-102 (tie-in) | F | F | F | F | F | MSY | F | O
2020
32 | 187 | 066/MOC/UTL/III/2020 | Inject Waste Mea to Incinerator | F | F | F | F | IP | EST | F | O | 38/ISO/MOC/III/2021
33 | 188 | 067/MOC/UTL/III/2020 | Modification Line FFW | F | F | F | F | F | EST | IP | O | IP |  | Dilanjut thn 2024
34 | 189 | 068/MOC/UTL/VII/2020 | Unloading propylene via iso tank | F | F | F | F | F | SGA | F | O
35 | 190 | 069/MOC/OCT/VIII/2020 | Rh Scavenger Process | F | C | C | C | C | WHO | C | O | Cancel
36 | 191 | 070/MOC/UTL/XI/2020 | Additional pump for inject waste mea to incenerator | F | F | F | IP | IP | YSY | F | O | 55/ISO/MOC/X/2021
37 | 192 | 071/MOC/UTL/XI/2020 | Loading IBD via Iso Tank | F | F | F | F | F | EST | F | O
38 | 193 | 072/MOC/UTL/I/2020 | Build a new N2 plant, provide tie in to N2 header line | F | F | F | F | F | EST | F | O
2021
39 | 194 | 073/MOC/OCT/V/2021 | Additional NBA reactor R-510B | F | F | IP | IP | IP | EST | IP | O | IP
40 | 195 | 074/MOC/SG/VII/2021 | Install TFM Camera Reformer - HTAS | F | F | F | F | F | YSY | F | O
41 | 196 | 075/MOC/UTL/VIII/2021 | Reservoir & Recycle water sewer | F | F | F | F | IP | AJW | F | O
42 | 197 | 076/MOC/OCT/VIII/2021 | Additional IBAL Purification System (T-170) | F | F | F | F | IP | NDJ | F | O
43 | 198 | 077/MOC/OCT/IX/2021 | Redundancy R-410B | F | F | IP | IP | IP | YMA | F | O
44 | 199 | 078/MOC/SGU/IX/2021 | Additional Evonik Membrane as Bank C | F | F | F | F | IP | YSY | F | O
45 | 200 | 079/MOC/SG/X/2021 | Additional New Lean MEA Pump LCO2 | F | IP | IP | IP | IP | NDJ | IP | O |  |  | Finished 2023
46 | 201 | 080/MOC/SG/X/2021 | Replacement Heat Exchanger E-009-1 | F | IP | IP | IP | IP | YSY | F | O
47 | 202 | 081/MOC/OCT/XII/2021 | Reposition IBAL Loading | F | F | F | F | IP | EST | F | O
48 | 203 | 082/MOC/OCT/XII/2021 | Modification Line H2SO4 | F | F | IP | IP | IP | BPR | IP | O |  |  | Finished 2023
49 | 204 | 083/MOC/UTL/1/2022 | Modification line N2 PKG | F | F | F | F | F | BPR | F | O | 58/ISO/MOC/XII/2022
2022
1 | 205 | 084/MOC/UTL/I/2022 | Additional new cell cooling tower | F | F | F | F | IP | NDJ | F | O
2 | 206
3 | 207 | 086/MOC/SG/III/2022 | Additional line NG process for fuel reformer | F | F | F | F | IP | YSY | F | O
4 | 208 | 087/MOC/UTL/III/2022 | Additional new flowmeter NG IAE to holder fuel | F | F | F | F | F | YMA | F | O | 57/ISO/MOC/XI/2022
5 | 209 | 088/MOC/SG/V/2022 | Modification line MDEA P-021 A/B | F | IP | IP | IP | IP | BPR | F | O
6 | 210 | 089/MOC/SG/IX/2022 | Additional and install switch to loading pump LCO2 | F | IP | IP | IP | IP | BPR | F | O
7 | 214 | 092/MOC/OCT/X/2022 | Additional NGS 97.0% to D-118 | F | IP | IP | IP | IP | BPR | F | O
8 | 215 | 093/MOC/OCT/X/2022 | Additional booster pump for make up solvent pressure unit A-110 | [10 empty] | Subject to review | bar: F F F to O O O
9 | 216 | 094/MOC/UTL/X/2022 | Additional control valve at B/L N2 from PKG | F | IP | IP | IP | IP | BPR | IP | O
10 | 217 | 095/MOC/UTL/XI/2022 | Dossing chemical facility of FFW pipeline | F | F | F | F | IP | BPR | F | O
11 | 218 | 096/MOC/UTL/XI/2022 | Additional of P-142C | F | IP | IP | IP | IP | YMA | IP | O
12 | 219 | 097/MOC/UTL/XI/2022 | Provide N2 high Pressure System | F | IP | IP | IP | IP | YMA | F | O
13 | 220 | 001/MOC/QCAS/XII/2022 | Installing fire protection in new substation | F | IP | IP | IP | IP | EDM | IP | O
2023
1 | 221 | 099/MOC/UTL/II/2023 | Additional line from reject RO to TK-821 | F | IP | IP | IP | IP | NDJ | IP | O |  |  | Finished
2 | 222 | 100/MOC/UTL/II/2023 | Side stream filter cooling tower Z-941 | F | IP | IP | IP | IP | YMA | F | O
3 | 223 | 101/MOC/UTL/III/2023 | Additional line feed stock to LCO2 from stack H-923 | F | IP | IP | IP | IP | BPR | IP | O |  |  | Finished
4 | 224 | 103/MOC/SG/IV/2023 | Installing CCTV in gate 2 (process area) | F | IP | IP | IP | IP | SCJ | F | O
5 | 225 | 104/MOC/UTL/IX/2023 | Installing separator for FOL | F | IP | IP | IP | IP | BPR | IP | O
6 | 226 | 105/MOC/UTL/IX/2023 | Improvement Incinerator H-851 | F | IP | IP | IP | IP | YMA | IP | O
7 | 227
8 | 228 | 107/MOC/UTL/X/2023 | Additional pretreatment in RO SWWT | F | IP | IP | IP | IP | YMA | IP | O
9 | 229 | 108/MOC/UTL/XI/2023 | Product RO SWWT to TK-923 | F | IP | IP | IP | IP | YSY | F | O
Note : F = Finished ; IP = In Progress ; N = Not Yet ; C = Cancel
H = HSE ; O = Operability ; D = Diversification